## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Customers found the checkout process quick, easy, and secure | 82% were satisfied
Customers | Went well | Customers signed up for the newsletter on the tablets | 78% signed up
Customers | Went well | Experience of Customers with tablet overall | 72% rated 4 or 5
Customers | Needs improvement | Waiting time | 54% have to wait 15+minutes whereas 20% have to wait for 11-15 minutes | Need discussions with GMs
Customers | Needs improvement | Technical issues with the tablet | 12% faced screen frooze out issues | Seydou needs to check and solve it.
Customers | Needs improvement | Preparation of correct order | 28% customers get wrong order | Need to discuss with Kitchen Manager to improve internal operatons
Project team | Went well | Tickets were easy to track and came through at a good pace
Project team | Went well | Guests seemed to get the hang of the tablets
Project team | Went well | Tablet instalation | tablet installation completed and working well in both locations
Project team | Needs improvement | Table turn time | Still the same | Need further analysis and discussion
Project team | Needs improvement | Orders got sent back | Some food order are geting sent back | Need further analysis and discussion
Project team | Needs improvement | Techinical issues | maintenance issues are popping out | Seydou need to check and fixed them
Project team | Needs improvement | Lack of understanding between front of house and back of house staff | back of house staff scale up their operations before the main launch | Need more comprehensive training
Project team | Needs improvement | Table implementation time | Tablet implementation took longer than expected | Need to plan and account for vacation time