## Tasks and Timeline
Sauce & Spoon Project Plan
| TASK |  | START DATE | DUE DATE | DURATION | TASK OWNER | STATUS | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | NOTES | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Tablets received
| Generate quotes and review costs |  |  |  | 14 | bar: WEEK 1 F to WEEK 2 T
| Create contracts and statements of work for vendors | Use past contracts for boilerplate |  |  | 5 | bar: WEEK 1 F to WEEK 2 T
| Order tablets | Shipping updated to ~10 days |  |  | 10 | bar: WEEK 2 W
2 | Milestone: Training complete
| Manager training planning |  |  |  | 5 | bar: WEEK 4 M to WEEK 4 R
| Manager training | One day event |  |  | 1 | bar: WEEK 4 M to WEEK 4 R
| GM meeting with staff regarding buy-in | Let Gilly plan this |  |  | 1 | bar: WEEK 4 F to WEEK 5 F
| Waitstaff training planning |  |  |  | 5
| Waitstaff training | One day event |  |  | 1
3 | Milestone: Tablet installation complete
| Book an electrician to install the tablets/wiring | Reference from Deanna |  |  | 8
| Install working tablets in the bar area at the Downtown restaurant locations |  |  |  | 1
| Install working tablets in the bar area at the North restaurant locations |  |  |  | 1
| Sync tablet software with POS | Need to update the POS system |  |  | 7
4 | Milestone: Launch Day complete
| Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 20
| Upload branding to tablets | Connect the marketing team to Terrific Tablets |  |  | 10
| Load menus into the tablets | Waiting on Carter |  |  | 7
| Include messaging about payment security on the tablet | Uploading text |  |  | 1
| Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  |  |  | 14
| Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 13
| Create and implement a post-dining survey to assess customer satisfaction |  |  |  | 3
| Test run planning |  |  |  | 10
| Test run | One day event |  |  | 1
| Launch day | One day event |  |  | 1